## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2024-04-08 | 14 | 2024-04-21 | 0 |  |  | Backend connection established and (User signup/login)
2 | 2024-04-22 | 14 | 2024-05-05 | 0
3 | 2024-05-06 | 14 | 2024-05-19 | 0
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2024-04-08 | 14 | 2024-04-21 |  | Planned |  | Database connection and the user login system, basic backend connections | 1
2 | 2024-04-22 | 14 | 2024-05-05 |  | Planned |  | Functional application with interactable features | 1
3 | 2024-05-06 | 14 | 2024-05-19 |  | Planned |  | Testing and designing polish | 1
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 99
Formulas:
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
ST1 | As a busy university student, I want to sync my class timetable with my personal calendar (Google, Apple, etc) so I can stay organised. | Done | 4 | 1 | High | Develop syncing feature for personal calendar.
ST3 | As a student, I want the web app to provide insights into potential timetable clashes (private and uni) so I can make adjustments in advance. | Removed | 7 | 1 | High | Show potential timetable clashes, ST1, linking to personal calendar will derive this function.
ST11 | As a student, I want the web app to save templates so I don't have to create recurring events from scratch. | Ongoing | 6 | 1 | High | Can save recurring events
ST15 | As a busy student, I want a streamlined view (by agenda / by month etc)to make providing feedback as quick as possible. | Done | 6 | 1 | High | Week, Month, Year, views
ST4 | As a student, I want the app to show me key university dates, so I know when the semester breaks are. | Done | 2 | 1 | Medium
ST16 | As a student, I want to print out a physical calendar with all my classes so it's more accessible. | Done | 6 | 1 | Medium | Output a physical calendar for printing out
ST5 | As a student, I want to be able to search upcoming key dates, so I know when to plan my holidays. | Ongoing | 5 | 2 | Medium
ST7 | As a student, I want to customise the look of my calendar to feel more specific and personalised to me. (Adding icons to papers) | Done | 6 | 2 | Low
ST10 | As a student, I want to be able to share events with my peers, so I can plan hangouts easily. | Done | 2 | 2 | Medium
ST6 | As a student preparing for exams, I want to sync my exam timetable with my personal calendar so I can plan my study schedule effectively prior to exams. | Done | 7 | 3 | High
ST8 | As a student I want to use a streamlined, simple aesthetic application. | Done | 6 | 3 | Low
ST9 | As a student I want to be able to view the weather forecast so I know when it rains | Done | 3 | 2 | Low
ST12 | As a student aiming to excel academically, I want the app to suggest study sessions based on my timetable and exam schedule to optimise my learning. | Planned | 7 | 3 | Low
ST14 | As a student I want to be able to create healthy habits based on available times in my calendar. | Planned | 4 | 3 | Low
ST2 | As a student, I want the app to automatically update my calendar with any changes to my timetable or exam schedule to avoid confusion. | Removed | 9 |  |  | You can add comments here to add key detail or explanation to the story. For larger definitions, use external tools and materials.
ST13 | As a group of students taking the same paper, we want suggestions for group study sessions where everyone is free. | Removed | 6 |  | Medium
ST17 | As a student with a hectic schedule, I want the app to send me reminders before each class and exam so I can stay on top of my academic commitments. | Removed | 8 |  | Low
ST18 | A button for Implementing syncing to google calender from front end |  | 6
100
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 101 |  | Sprint count | 3
Count trend from last |  |  | 3 | sprints | Trend sprint count | 4
[5 empty] | Trend offset | 1 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 26 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 35 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 35 |  | Trend count | 4 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 35 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 35 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 33.5 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 4
Original estimate - Max |  |  | 7 |  | Standard Dev. | 6.0828
3 |  |  | 3
Realized average |  |  | 3 |  | LastPlanned | 28
Average last 8 |  |  | 3 |  | LastRealized | 28
Avg. worst 3 in last 8 |  |  | 3
Trend |  |  | 3
Realized + St. Dev |  |  | 3
Realized - St. Dev |  |  | 3
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 94 | 45 | 38 | 56 | 94 | 94 | 0 | 0 | 94 | 87.6667 | 87.6667 | -11 | 35 | 35 | 35
2 | 56 | 32 | 39 | 28 | 56 | 56 | 0 | 0 | 56 | 54.1667 | 54.1667 | -11 | 35 | 35 | 35
3 | 28 | 28 | 28 |  | 17 | 17 | -11 | -11 | 17 | 20.6667 | 20.6667 | -11 | 35 | 35 | 35
4 |  |  |  |  | -11 | -11 | -11 | -11 | -11 | -11 | -11 | -11 | 35 | 35 | 35
5 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
6 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
7 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
8 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
9 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
10 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
11 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
12 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
13 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
14 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
15 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
16 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
17 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
18 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
19 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
20 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
21 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
22 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
23 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
24 | [9 empty] | -11 |  | -11 | 35 | 35 | 35
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 45 | 45 | 36 | 7
Task rows | 12 | Done days | 3 |  | 45 | 36 | 27 | 18 | 9
Warning! These are necessary |  | Trend |  |  | 48.3333 | 29.3333 | 10.3333
template rows |  | Trend Days | 3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 48.3333 1: 1; 29.3333 2: 2; 10.3333 3: 3; 10.3333 4: 4; 10.3333 5: 5
Syncing calendar feature with Google cal | 1 | James | Done | 4 | 48.3333 1: 4; 29.3333 2: 2; 10.3333 3: 0
Evision and Personal Calendar clashes (show a warning message) | Deleted |  | Cancelled | 0 | 48.3333 1: 0
Can save recurring events | 11 |  | Done | 6 | 48.3333 1: 6; 29.3333 2: 12; 10.3333 3: 0
Calendar viewing (Weekly,Monthly) | 15 | Sam | Done | 6 | 48.3333 1: 6; 29.3333 2: 9; 10.3333 3: 0
Physical Calendar output | 16 | Yuki | Done | 6 | 48.3333 1: 6; 29.3333 2: 0; 10.3333 3: 0
Database connection signing in (Supabase) | Null | Sam , Shreya | Done | 4 | 48.3333 1: 4; 29.3333 2: 0; 10.3333 3: 0
CSS (Hamburger Menu Styling) | Null | Cyrus | Done | 3 | 48.3333 1: 3; 29.3333 2: 3; 10.3333 3: 0
Login page | Null | Sam | Done | 3 | 48.3333 1: 3; 29.3333 2: 0; 10.3333 3: 0
Signup Page | Null | Shreya | Done | 3 | 48.3333 1: 3; 29.3333 2: 0; 10.3333 3: 0
Show key dates on calendar (from otago key dates) | 4 |  | Ongoing | 4 | 48.3333 1: 4; 29.3333 2: 4; 10.3333 3: 4
Profile settings page (Welcome message) | Null | Shreya, Yuki | Ongoing | 3 | 48.3333 1: 3; 29.3333 2: 3; 10.3333 3: 3
Database connection Events in (Supabase) | Null |  | Done | 3 | 48.3333 1: 3; 29.3333 2: 3; 10.3333 3: 0
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 39 | 39 | 21 | 16
Task rows | 9 | Done days | 3 |  | 39 | 31.2 | 23.4 | 15.6 | 7.8
Warning! These are necessary |  | Trend |  |  | 36.8333 | 25.3333 | 13.8333 | 2.3333
template rows |  | Trend Days | 3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 36.8333 1: 1; 25.3333 2: 2; 13.8333 3: 3; 2.3333 4: 4; 2.3333 5: 5
Testing Signup |  |  | Ongoing | 5 | 36.8333 1: 5; 25.3333 2: 5; 13.8333 3: 5
Testing DatabaseTables |  |  | Done | 5 | 36.8333 1: 5; 25.3333 2: 5; 13.8333 3: 0
Testing Login |  |  | Ongoing | 5 | 36.8333 1: 5; 25.3333 2: 5; 13.8333 3: 5
Log out button |  | James | Done | 4 | 36.8333 1: 4; 25.3333 2: 0
Show key dates on calendar (from otago key dates) |  | James | Done | 4 | 36.8333 1: 4; 25.3333 2: 0
Profile settings page (Welcome message) |  |  | Planned | 3 | 36.8333 1: 3; 25.3333 2: 3; 13.8333 3: 3
CSS styling |  | Cyrus | Ongoing | 3 | 36.8333 1: 3; 25.3333 2: 3; 13.8333 3: 3
Exam dates inputting to events |  | James | Done | 7 | 36.8333 1: 7; 25.3333 2: 0
Integrating weather |  | Sam | Done | 3 | 36.8333 1: 3; 25.3333 2: 0
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 28 | 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Task rows | 7 | Done days | 1 |  | 28 | #REF! | #REF! | #REF! | #REF!
Warning! These are necessary |  | Trend |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
template rows |  | Trend Days | #REF! |  | #REF! | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1 | 2 | 3 | 4 | 5
Testing Signup | NULL |  | Planned | 5 | 5
Show the key dates and exam dates on the dashboard calendar. | 4 |  | Planned | 5 | 5
Testing Login | NULL |  | Planned | 5 | 5
Google syncing | 1 | James | Ongoing | 4 | 4
Physical Calendar page UI improvement | 16 | Yuki | Ongoing | 3 | 3
Profile settings page (Welcome message) | NULL |  | Planned | 3 | 3
Final Improvements | NULL | Everyone | Ongoing | 3 | 3
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.