## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2024-04-08 | 14 | 1970-01-01 12:00 | 0 |  |  | Backend completed
2 | 1970-01-01 12:00 | 14 | 1970-01-01 12:00
3 | 2024-05-06 | 14 | 1970-01-01 12:00
1970-01-01 12:00
1970-01-01 12:00
1970-01-01 12:00
1970-01-01 12:00
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2024-04-08 | 14 | 1970-01-01 12:00 |  | Planned |  | Database connection and the user login system, basic backend connections | 1
2 | 1970-01-01 12:00 | 14 | 1970-01-01 12:00 |  | Planned |  | Functional application with interactable features | 1
3 | 1970-01-01 12:00 | 14 | 1970-01-01 12:00 |  |  |  | Testing and designing polish | 1
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
| 1970-01-01 12:00 |  | 1970-01-01 12:00
Unallocated stories
Formulas:
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
ST1 | As a busy university student, I want to sync my class timetable with my personal calendar (Google, Apple, etc) so I can stay organised. | Planned | 4 | 1 | High | Develop syncing feature for personal calendar.
ST3 | As a student, I want the web app to provide insights into potential timetable clashes (private and uni) so I can make adjustments in advance. | Planned | 7 | 1 | High | Show potential timetable clashes
ST11 | As a student, I want the web app to save templates so I don't have to create recurring events from scratch | Planned | 6 | 1 | High | Can save recurring events
ST15 | As a busy student, I want a streamlined view (by agenda / by month etc)to make providing feedback as quick as possible. | Planned | 6 | 1 | High | Week, Month, Year, views
ST4 | As a student, I want the app to show me key university dates, so I know when the semester breaks are. | Planned | 2 | 1 | Medium
ST16 | As a student, I want to print out a physical calendar with all my classes so it's more accessible. | Ongoing | 6 | 1 | Medium | Output a physical calendar for printing out
ST5 | As a student, I want to be able to search upcoming key dates, so I know when to plan my holidays. | Planned | 5 | 2 | Medium
ST7 | As a student, I want to customise the look of my calendar to feel more specific and personalised to me. (Adding icons to papers) | Planned | 6 | 2 | Low
ST10 | As a student, I want to be able to share events with my peers, so I can plan hangouts easily. | Planned | 2 | 2 | Medium
ST6 | As a student preparing for exams, I want to sync my exam timetable with my personal calendar so I can plan my study schedule effectively prior to exams. | Planned | 7 | 3 | High
ST8 | As a student I want to use a streamlined, simple aesthetic application. | Planned | 6 | 3 | Low
ST9 | As a student I want to be able to view the weather forecast so I know when it rains | Planned | 5 | 3 | Low
ST12 | As a student aiming to excel academically, I want the app to suggest study sessions based on my timetable and exam schedule to optimise my learning. | Planned | 7 | 3 | Low
ST14 | As a student I want to be able to create healthy habits based on available times in my calendar. | Planned | 4 | 3 | Low
ST2 | As a student, I want the app to automatically update my calendar with any changes to my timetable or exam schedule to avoid confusion. | Removed | 9 |  |  | You can add comments here to add key detail or explanation to the story. For larger definitions, use external tools and materials.
ST13 | As a group of students taking the same paper, we want suggestions for group study sessions where everyone is free. | Removed | 6 |  | Medium
ST17 | As a student with a hectic schedule, I want the app to send me reminders before each class and exam so I can stay on top of my academic commitments. | Removed | 8 |  | Low

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 101 |  | Sprint count
Count trend from last |  |  | 3 | sprints | Trend sprint count
[5 empty] | Trend offset | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 26 | [11 empty] | (or planned) implemented functionality at the beginning of each sprint.
25569.5 | [14 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  |  |  | Trend count | [9 empty] | (i.e. if the amount of story points
Average last 8 | [14 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 | [14 empty] | of the bars indicate the estimated size of the project at the
Trend | [14 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [9 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min
Original estimate - Avg
Original estimate - Max |  |  |  |  | Standard Dev.
25569.5
Realized average |  |  |  |  | LastPlanned
Average last 8 |  |  |  |  | LastRealized
Avg. worst 3 in last 8
Trend
Realized + St. Dev
Realized - St. Dev
[5 empty] | Trend | [6 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 101 | 29 | 29 |  |  |  | 0
2 |  | 20 | 20
3 |  | 29 | 29 | 101
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## Sp1
2
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals
Task rows |  | Done days
Warning! These are necessary |  | Trend
template rows |  | Trend Days |  |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1
Syncing feature | 1 | James | Ongoing | 4 |  | 2: 2; 3: 0
Timetable clashes | 3 |  | Planned | 7 |  | 2: 7; 3: 2
Event templates | 11 |  | Planned | 6 |  | 2: 12; 3: 12
Calendar viewing (Weekly,Monthly,Yearly) | 15 |  | Planned | 6 |  | 2: 9; 3: 9
Physical Calendar output | 16 | Yuki | Ongoing | 6
Database connection (Supabase) | Null | Sam , Shreya | Ongoing | 4
CSS | Null | Cyrus | Ongoing | 3
Login page | Null | Sam |  | 3
Signup Page | Null | Shreya |  | 3
Show key dates on calendar | 4 |  |  | 2

## Sp2
2
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals
Task rows |  | Done days
Warning! These are necessary |  | Trend
template rows |  | Trend Days |  |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1